# CubIQ Services Migration Plan

## 1. Objective

Rebrand, migrate, and modernize the existing Market Risk automation services into the CubIQ Platform, ensuring consistency, maintainability, and alignment with new infrastructure standards.
 The approach prioritizes reuse of existing work, code cleanup, removal of legacy dependencies, and alignment to SPN-based authentication, Kubernetes deployment, and standardized CI/CD.

## 2. Target Milestones

| Milestone | Deadline |
| --- | --- |
| All services deployed to QA | 31 January 2026 |
| Production Deployment | 28 February 2026 |

## 3. Scope — Services Included

- CubIQ Metadata Catalog

- CubIQ Semantic Processor

- CubIQ MRV Calculation Engine

- CubIQ PBI Deployment Service

- CubIQ Data Refresh Controller

- CubIQ Recon Service

## 4. Migration Phases & Timeline

| Phase | Timeline | Summary |
| --- | --- | --- |
| Phase 1 — Assessment & Planning | Nov 2025 | Confirm reusable functionality, dependencies, and required refactoring. Define CubIQ namespaces, repository layout, and access requirements. |
| Phase 2 — DevOps, Identity & Infrastructure Setup | Nov 2025 | Create GitLab repositories, shared CI/CD pipelines, Helm templates, and AKS integration. Create SPNs for each environment and provision access to Power BI, Databricks, SQL MI, Key Vault, and event orchestration services. |
| Phase 3 — Development, Refactor & Alignment | Dec 2025 – Jan 2026 | Migrate existing code into new CubIQ Visual Studio solutions. Update namespaces, remove unused legacy logic, optimize code, and standardize configuration. Integrate services with the new deployment model. |
| Phase 4 — Integration, Validation & Hardening | Jan 2026 | Validate full end-to-end functionality: metadata → semantic build → MRV generation → deployment → refresh → reconciliation. Conduct performance testing and finalize observability and resiliency. |
| Phase 5 — Production Readiness & QA Completion | Feb 2026 | Final QA cycles, regression testing, security validation, reliability checks, operational readiness sign-off, and release packaging. |
| Phase 6 — Production Cutover & Stabilization | February 2026 (Go-Live: Feb 28) | Deploy to PROD. Enable monitoring and recon in parallel validation mode. Address post-deployment adjustments and begin decommissioning legacy components. |

## 5. Identity & Access Requirements

One Service Principal per environment will be created and secured:

- spn-cubiq-dev

- spn-cubiq-qa

- spn-cubiq-preprod

- spn-cubiq-prod

Required resource access includes:

- Power BI (workspace, XMLA, dataset operations)

- Databricks (SQL endpoints + workspace access)

- SQL MI (read/write roles as needed)

- Event orchestration services (send/listen rights)

- Azure Key Vault (Get/List Secret permissions)

All credentials will be managed via CI/CD → Helm → AKS workload identity, with no secrets embedded in code.

## 6. Deliverables

- Six CubIQ services deployed and running in QA by January 31, 2026

- Fully containerized services aligned with new namespace and standards

- Centralized CI/CD and Helm charts per service with shared templates

- Operational runbooks and service documentation

- Production deployment completed by February 28, 2026

## 7. Governance & Reporting

- Migration Owner: Julio Diaz

- Tracking Method: GitLab Epics → Milestones → Issues

- Review Cadence:

  - Weekly engineering check-in

  - Monthly delivery update to management